## Slide 1: Chapter 5
Life-Cycle Phases
From
Software Project Management
By
Walker Royce (of IBM)
And Slides on Spiral by Barry Boehm

## Slide 2: Introduction
On one hand,
  Do we spend far too much time on analyses and paper studies?
  Do we delay actually doing the builds: the development baselines?
  Very easy to do… Some feel in general that this is true…
On the other hand,
  Do we jump into designs and coding, and hack the heck out of an application in attempts to get it to work?
  Lots of people think we do this too….
Class discuss:
  What do you do?
  What do you think corporations think they do?

## Slide 3: Introductory Statement:
Walker Royce feels that we need BALANCE between research and development (R&D) and production activities
Need some kind of balance between:
  Concentrating on capturing and modeling functionality and
  Building a robust product that has the performance, reliability, and scalability customers desire….
We are after a development life-cycle BALANCE…

## Slide 4: Finer Granularity
Further, we need a process that supports this balance.
Need this stated more precisely:
 Need a process to help balance:
  Planning, capturing, and modeling requirements and establishing a baseline architecture,
with
  Continuous assessment, measuring risk, and testing to ensure progress and quality
with
  Evolution and verification of the application’s functionality through series of customer demonstrations and ultimate validation.

## Slide 5: Engineering and Production Stages
Royce claims to achieve the ROI for software development, we need to use a ‘manufacturing process’ that is characterized by the
  highest utilization of automated development tools and
  use of component-based approaches to development.
He likens a desirable software process to a manufacturing process:

## Slide 6: Engineering and Production Stages
He breaks all activities down into
  Engineering and Production
Engineering work: This centers on risk reduction, prototyping, establishing architectural baseline, assessment, analysis, design, and planning…
  Implies a smaller team up front.
Production work: programming and unit test, system and integration testing, demonstrations, assessment, base-lining configuration, and releases; operations
  Note that production includes operations…

## Slide 7: Two Stages: Far Too Abstract
BUT, he argues a life cycle of two stages is far too abstract to track the many detailed activities – all with actors, activities, and artifacts….
So, he maps Rational Unified Process (RUP) Phases into these more comprehensive phases.
  Enter: Engineering Phase = Inception and Elaboration
  Enter: Production Phase = Construction and Transition
Engineering, i.e., Inception and Elaboration, focuses on the concept (idea) of the application and its architectural components (analysis and preliminary design – perhaps a wee bit of detailed design)
  Artifacts are established and base-lined; (Configurations…)
Production, i.e., Construction and Transition, focuses on programming, testing, releases and converting / establishing operational capabilities
  Implies that artifacts from earlier stage (engineering) more difficult to change as activities more ‘downstream activities’ occur

## Slide 8: Spiral Model - Overview
Spiral Model is another incremental model.
Embraces (well known for these:)
  prototyping,
  iterative software development, and
  risk assessment.
Model is graphed like a spiral.
Development can be halted at the end of any cycle…depending on evaluation of previous ‘cycle.’

## Slide 9: Spiral Model
Very much a Risks-Driven Approach
Different idea of software development.
How does this project affect the developers
and the clients?
How does each step in the project affect
its overall development?
Not used in previous development models.
  They were usually code-driven or document-driven.

## Slide 10: Previous Software Process Models
An evolution of models
  –Code & Fix
  –Stagewise & Waterfall
  –Evolutionary Development.
Code & Fix
• First, elementary model
• Write code now; fix it later
• No planning involved
• Problems:
– Code is poorly structured.
– The software developed was usually a poor match for users’ needs.

## Slide 11: Stagewise & Waterfall
Born out of the shortsightedness of the Code & Fix model.
  - need for a design phase, requirements phase,
and a testing phase.
First used to develop SAGE (Semi-Automated Ground Environment), an early warning system for the Cold War era.
The Semi-Automatic Ground Environment (SAGE) was a system of large computers and associated networking equipment that coordinated data from many radar sites and processed it to produce a single unified image of the airspace over a wide area. SAGE directed and controlled the NORAD response to a Soviet air attack, operating in this role from the late 1950s into the 1980s. Its enormous computers and huge displays remain a part of cold war lore, and a common prop in movies such as Dr. Strangelove and Colossus.

## Slide 12: Stagewise
A development process of successive phases.
– Phases included operational plan, operational
specs, coding specs, coding, parameter
testing, assembly testing, shakedown, system
evaluation.
Underwent two refinements in 1970.
Now referred to as the Waterfall Model.

## Slide 13: Waterfall Model
Introduced:
– Feedback loops across multiple stages:
Validation and verification steps.
– Prototyping via a “build it twice” step alongside of
requirements and design.
• Difficulties exposed even as revisions were made to
the model.
– Required elaborated documents. (Document- driven; lengthy development cycles, etc.
– Led to pursuing stages of development in the wrong order

## Slide 15: Evolutionary Development
Evolution of the system in directions based on experience.
  Provides rapid initial operational capability.
“I can’t tell you what I want, but I’ll know it when I see it.”
Flexible, yet uncertain approach.
Evolutionary Development Problems:
No formal design phase (same problem as Code & Fix).
One bad assumption – the unplanned paths “will” be compatible.
Hard-to-change code resulted.
Many problems when new software was incrementally replacing old software

## Slide 17: Spiral Model - Overview
In the Spiral Model, prototyping, evaluation, planning, and all engineering and production activities are executed in different quadrants. (Different variations of the model…)
But the basic notion of iteration is very firmly established.
For each ‘cycle’:
  risk is assessed,
  more design and development is undertaken,
  the work products and evaluated, and
  planning for the next cycle in the spiral is undertaken;
  Iterate…..
Please note that in reality, the Spiral Model curve is actually skewed to the right, as the spirals do not ‘carve’ out equal ‘areas.
Area in each cycle is a determinant of effort and cost….

## Slide 18
R & D Stage
Inception
Elaboration
Construction
Transition
Production Stage
Idea
Architecture
Beta Releases
Products
Prototypes
artifacts
Major risk items
Creative, judgment
Business Rules
Stakeholder Vision
Change managed baselines
Elaborate artifacts
Low Risk Items
Engineering, reasoned
  Well-instrumented processes
‘Skewness:
Spiral Model and the RUP Phases

## Slide 19: Back to our Process Model (Rational Unified Process)
Let’s look more closely at the phases for our process model:
  Inception
  Elaboration
  Construction
  Transition
Each phase has
  primary objectives,
  essential activities, and
  primary evaluation criteria
to judge its success at milestone time.
Since the process that is underpinning our management of software processes and personnel course is the RUP, it is imperative that we understand this management process, the RUP, as much as possible

## Slide 20: Inception Phase (1)
Overriding Goal: achieve concurrence among stakeholders on life-cycle objectives for the project (milestone: LCO)
Primary Objectives: (by end of phase…)
  Establish project software scope and boundary conditions
    Includes operational concept, acceptance criteria, and a clear understanding of what is and what is not intended in the product
  Identify critical use cases (core functionalities) of system and the primary scenarios that will drive the activities
  Demonstrate at least one candidate architecture against some of the primary scenarios (walk through it…)
  Estimate the cost and schedule for the entire project (including detailed estimates for the elaboration phase)
  Estimate potential risks (sources of unpredictability)
Know These!

## Slide 21: Inception Phase (2)
Essential Activities
  Develop Project Scope
    Capture requirements and concept of operations  repository
      Describes users’ view of the requirements
      Repository contains information used to define problem space
      Repository must contain information to capture acceptance criteria
  Develop a Candidate Architecture and Demonstrate it
    Repository contains enough information to demonstrate at least a single candidate architecture
      This might be at a very high level, such as deployment level;
      A general layered architecture may also be demonstrated.
      But considerable Requirements have not yet been done and almost NO Analysis and Design have been undertaken.
    Repository must include enough data to support make/buy decisions so that cost, schedule, resources can be ‘costed out.’
  Planning and Preparing the Business Case
    Risk management strategies, staffing, general iteration plans, cost/schedule/profitability tradeoffs are all evaluated.
    Environmental (Infrastructure) support is defined.
    ROI, market share, etc.

## Slide 22: Elaboration Phase (1)
Clearly the most important phase! Overriding goals are several, varied, and critical!
   At end of phase:
    engineering is complete,
    almost all use cases are designed (certainly all critical use cases and flows),
    a prototype for gathering requirements and to demonstrate proof of concept is accommodated, and
    an analysis model is constructed, and
    a baseline executable architecture is established and demonstrated.
  Risks have to have been addressed and strategies understood;
  Business Rules have been subscribed to closely;
  Cost and schedule are acceptable and predictable and updated, if necessary,
  Stakeholder acceptance is achieved (the vision is realized in the artifacts), etc. and
  We have stability…
   We want to graduate from a low-cost effort into a full-blown production process, where costs are maxed and personnel are on staff.

## Slide 23: Elaboration Phase (2)
 Primary Objectives (at end of phase…)
  Base-lining the architecture asap (establishing configuration management procedures…for tracking all artifacts!
  Base-lining the Vision. It is now ‘solid’ and accommodated in the artifacts so far.
  Base-lining a detailed plan for Construction
  Demonstrating the baseline architecture such that it clearly supports the vision – at, of course, reasonable cost in reasonably time.

## Slide 24: Construction Phase (1)
Great mindset change: now interested in producing a deployable product! (implementation)
  iterate, iterate…, integrate/assess/plan as we go.
  No longer ‘engineering;’ rather, production!!!
Need to manage resources, control operations to optimize costs, schedules, and quality.
Emphasis on the development of intellectual property shifts to the reality of usable products.

## Slide 25: Construction Phase (2)
One very nice attribute in Construction:
  Parallel development
    Based on architecture…do homework up front!!!!
    Accelerates delivery of deployable releases
    Downside: complicates project management and synchronization of teams, integration, and workflow.
  Architecture will drive this
    A good architecture will support parallel development
    Emphasized during Elaboration – planning for Construction.

## Slide 26: Transition Phase
Phase concludes when the baseline realizes the original vision and we are ready to put it in the users’ hands.
Might be end of project development or starting point for next cycle, or starting point for next version of deployable version...
Might be forwarding ‘whole shooting match’ over to
  the maintenance group or
  third party for future work…

## Slide 27: Transition Phase
Transition is not uncomplicated
May involve several iterations including
  Beta1, beta2, testing and ‘levels’ of releases (all releases may not be equal)
    Custom software?
    Conversion software?
  Development of user documentation,
  User training, especially in initial use of product
    Web-X; on developer’s site; on client’s site.
    Who pays for what? How does this work? Millions!!!
  Usability problems and tuning,
  (Un)solicited feedback, and more….

## Slide 28: Transition Phase
Essential Activities
  “Synchronization and integration of concurrent construction increments into consistent deployable baselines” – ensure all flows…
  Installation / Conversion
    Cut over (complete switch to new application)
    Run in parallel, or
    Phased…
  Assessment against vision and acceptance criteria.
Evaluation Criteria
  Is user satisfied?
  Are actual expenditures reasonably close to planned expenditures?

## Slide 29: Summary - Know These
Recognize each phase has one or more iterations
Phases end with major milestones; (Know these!)
Iterations within phases have minor milestones.
  Each have deliverable(s) and undergoes assessment against criteria
  Each iteration entails a sequence of activities that culminate in a minor milestones or major milestones (if iteration ends phase)
  Scope and results of iterations are captured via artifacts produced.

## Slide 30: Summary (continued) – Know!
Major Milestones (phase end):
  Approved by stakeholders
  Map to significant management/business decisions rather than to completion of a specific software development activity.
Minor milestones (iteration end):
  Approved internally and
  Realized by artifacts / new versions of artifacts in repository;
  internal synchronization,
  internal assessment,
  Additional planning take place…
  ‘Executable’ releases (not necessary deployable…)

## Slide 31: Lessons Learned – Organizational Change
Middle management is where the war is won
  Championed by respected leaders who own the plan and execution.
  Project Management: Can be immense pressures from above (Sr. Management) and different sets of problems/issues from below (actual developers)
ROI on first implementation
  Disruption costs must be absorbable in the benefit
Implemented on business critical project
  This is where the A-players are
Success breeds success – (like the NFL)
  First increment needs to be ambitious, but realistic
Results drive incentives
  Such as: milestone demonstrations, release timeliness, release content, etc
  Not: processes, methods, expended energy, reuse, audits, meetings, subjective assessments, document production,…